Project Plan

Project Name:

Project Management Improvement Project

Example

Disclaimer

This example is based on a real project. However, this version is changed to present full examples of Project Plan components as described in the DoIT Project Management Framework. This example is not a true representation of the project plan for the Project Management Improvement project.

Prepared By:  Name1 - Project Manager

Title:  Project Manager

Date:  March 7, 2007

Project Plan Approval Signatures

Project Name:  GymTracker Web Application Development Project

Project Manager

________Vladyslav Urbanskyi__________     	 _________10.03.2026________

(Signature)						 (Date)

Name1 - Project Manager

DoIT Project Manager

Division of Information Technology – Systems Engineering and Operations

Project Sponsor

_____Dmytro Pavliuk________     	 _______10.03.2026______

(Signature)						 (Date)

Name2 - Project Sponsor

DoIT Process Manager

Division of Information Technology – CIO Office

Executive Sponsor

________ Dmytro Pavliuk__________       	 _____10.03.2026_____

(Signature)						 (Date)

Name3 - Executive Sponsor

Associate CIO

Division of Information Technology – CIO Office

Document Change Control

The following is the document control for revisions to this document.

| Version Number | Date of Issue | Author(s) | Brief Description of Change |
| --- | --- | --- | --- |
| V1.0 | 25.02.2026 | V. Urbanskyi | Initial draft of the Project Charter. |
| V1.1 | 02.03.2026 | D. Pavliuk | Added Project Scope and Stakeholder roles. |
| V1.2 | 10.03.2026 | V. Urbanskyi | Updated Milestones and Deliverables sections. |

Definition

The following are definitions of terms, abbreviations and acronyms used in this document.

| Term | Definition |
| --- | --- |
| CIO | Chief Information Officer |
| DoIT | Division of Information Technology |

Table of Contents

1. Project Plan Overview and Critical Assumptions	1

2. Project Work Plans	2

2.1 Work Breakdown Structure	2

2.2 Staffing Plan	3

2.3 Project Schedule	6

2.4 Project Budget	8

3. Project Control Plans	9

3.1 Communications Plan	9

3.2 Quality Management Plan	9

3.3 Change Management Plan	9

3.4 Issue Management Plan	9

3.5 Risk Management Plan	9

Appendix	10

A – Review Team	10

B – Communications Plan	10

C – Quality Management Plan	10

D – Change Management Plan	10

E – Issue Management Plan	10

F – Risk Management Plan	10

# 1. Project Plan Overview and Critical Assumptions

The purpose of the Project Plan is to present the detail required to successfully execute and control the project, facilitate communication among project stakeholders, and document approved schedule baselines. The project plan is a living document and is expected to change over time as more information about the project becomes available.

The project plan was developed based upon certain key assumptions as noted in the Project Charter. Any changes to these assumptions may impact the project schedule, projected costs, the project scope and/or the project quality. These assumptions are:

- The goals of this project support the vision, mission, and goals of DoIT, helping faculty, staff and students realize their visions through the use of information technology.

- The project helps DoIT achieve its goal of outstanding customer service.

- DoIT management actively supports improvements in each of the seven component areas: framework, tools, project management skills, thinking, culture, politics, and communication.

- DoIT management and staff comply with specifications for all project management responsibilities as stated in the “Project Management at DoIT – A Social Contract” document.

- The timeline is reasonable and doable. The phased rollout supports early success and continued improvement.  The project includes a lengthy implementation as components are developed and implemented, followed by sustained competency and improvements in the seven component areas.

- DoIT management assigns key project roles and adequate budget for the development and implementation of this project.

- Effective, adequate, and appropriate levels of communication occur between DoIT management, the sponsor, and the project team during all phases of the project.

- The framework deliverable avoids excessive detail to ensure common understanding, flexibility, and adoption.

- The deliverables of the project are implemented DoIT-wide, supporting many diverse functional groups, projects, and customers.

# 2. Project Work Plans

## 2.1 Work Breakdown Structure

## The work breakdown structure identifies the project’s tasks to provide a framework for organizing and managing the work of the project.

| Project Management Initiative Phase I Initiate Project Develop Project Charter Plan Project Develop Work Plan Develop Project Control Plan Finalize Project Plan and Gain Approvals Develop Work Breakdown Structure Develop Project Staffing Plan Develop Project Schedule Develop Project Budget Develop Quality Management Plan Define Scope Define Requirements Define High-Level Roles Define High-Level Budget Identify High-Level Control Strategies Finalize Charter Develop Communication Plan Execute and Control Project Design Content formats Build the Framework Test the Framework Implement the Framework Close the Project Design the Framework Define stages and activities Design web Delivery Tool Write the content Review content for quality Build web tool prototype Test web tool usability Test content usability Adjust tool and content based on feedback Move web tool to production environment Announce Tool availability Conduct post project review Celebrate |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

## 2.2 Staffing Plan

The purpose of the staffing plan is to make certain the project has sufficient staff with the right skills and experience to ensure a successful project completion.

Role Requirements

The following is a detailed breakdown of the roles required to execute the project. It includes: the project role, the project responsibility of the role, skills required, number of staff required to fulfill the role, the estimated start date and the expected duration the staff resource will be needed on the project.

| Role | Project Responsibility | Skills Required | Number of Staff Required | Estimated Start Date | Duration Required FY05-06 |
| --- | --- | --- | --- | --- | --- |
| Project Team |  |  |  |  |  |
| Project Manager | Lead team, report status | Project Management | 1 | 7/1/26 | 6 months |
| Core Team | Review deliverables, assure quality | Project Management | 1 | 9/1/26 | 4 months |
| Content Developer | Create framework content | Research and web writing skills | 1 | 9/1/26 | 4 months |
| Web Designer | Design web-based performance mgmt tool | Web design, web writing skills | 1 | 10/1/26 | 3 months |
| Web Developer | Build the web-based performance management tool | Web development | 1 | 11/1/26 | 2 months |
| Review Team | Evaluate deliverables, promote use | Project Management experience | 1 | 11/1/26 | 2 months |

Staff Assigned to Roles

The following is a detailed breakdown of the actual staff assigned to the project role, the amount of Full Time Equivalent (FTE) requested for the role, the actual FTE acquired, the labor rate and unit of the labor rate for the resource and the source from which the resource is recruited.

| Role | Name | Requested FTE FY05-06 | Acquired FTE FY05-06 | Rate | Rate Unit | Source |
| --- | --- | --- | --- | --- | --- | --- |
| Project Team |  |  |  |  |  |  |
| Project Manager | V. Urbanskyi | 1.00 | 1.00 | $85 | hour | DoIT - Systems Engineering Operations |
| Core Team | D. Pavliuk | .10 | .10 | $70 | hour | DoIT- Network Services |
|  | D. Pavliuk | .10 | .10 | $70 | hour | DoIT – Enterprise Internet Services |
|  | D. Pavliuk | .10 | .10 | $70 | hour | DoIT–Data Resource Management Technologies |
| Content Developer | D. Pavliuk | .90 | .90 | $70 | hour | DoIT–Data Resource Management Technologies |
| Web Designer | D. Pavliuk | .05 | .05 | $75 | hour | Academic Technology Solutions |
| Web Developer | D. Pavliuk | .05 | .00 | $65 | hour | Academic Technology Solutions |
| Review Team (20 reviewers) | V. Urbanskyi | .10 | .10 | $70 | hour | See Appendix A for detail list |
| Total |  | 2.40 | 2.35 |  |  |  |

Staff Resource Loading Chart

The following includes the estimated effort in Full Time Equivalent (FTE) days required by month for each staff resource assigned to the project.

|  | FY05-06 FTE in Days |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Role | Number of Staff Required | July | Aug | Sept | Oct | Nov | Dec | Total |
| Project Manager | 1 | 15.00 | 15.00 | 15.00 | 15.00 | 15.00 | 15.00 | 90.00 |
| Core Team Members | 1 | 5.00 | 10.00 | 15.00 | 15.00 | 4.50 | 4.50 | 18.00 |
| Content Developer | 1 | 5.00 | 10.00 | 15.00 | 15.00 | 13.50 | 13.50 | 54.00 |
| Web Designer | 1 | 5.00 | 10.00 | 15.00 | 3.50 | 1.50 | 1.50 | 6.50 |
| Web Developer | 1 | 5.00 | 10.00 | 2.00 | 2.00 | 5.00 | 5.00 | 10.00 |
| Review Team | 1 | 2.00 | 10.00 | 2.00 | 2.00 | 10.00 | 10.00 | 20.00 |
| Total | 6 | 37.00 | 65.00 | 64.00 | 47.00 | 49.50 | 49.50 | 198.50 |

Training Needs

The following are the detailed training needs to bring staff to a level of skill required for project execution.

| Role/Staff Resource | Training Need | Timeframe Needed | Anticipated Cost | Suggested Vendor/Method |
| --- | --- | --- | --- | --- |
| D. Pavliuk | Writing For Web | By 10/1/26 | $2000 | Vendor - Information Mapping |

### PROJECT ORGANIZATION CHART

The project organization chart is a graphical picture of the organization and reporting relationships of the project.

DoIT Management

DoIT

CIO Office

Stakeholder

Round Table

Stakeholder

Operations Directors

Project Sponsor

V. Urbanskyi

Stakeholder

Tech Directors

Project Manager

V. Urbanskyi

Stakeholder

MTeam

Project Team

D. Pavliuk

D. Pavliuk

D. Pavliuk

D. Pavliuk

D. Pavliuk

D. Pavliuk

## 2.3 Project Schedule

This section includes a Gantt chart and a project schedule for the project.

Gantt Chart

The Gantt chart graphically represents a project by showing each task as a horizontal bar whose length is the time needed to complete the task.

|  | Project Management Improvement Project – Phase 1 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2026 |  |  |  |  |  |  | 2026 |
|  |  | June | July | August | Sept | Oct | Nov | Dec | Jan |
| 1 | Initiate Project |  |  |  |  |  |  |  |  |
| 1.1 | Develop Project Charter |  |  |  |  |  |  |  |  |
| 2 | Plan the Project |  |  |  |  |  |  |  |  |
| 2.1 | Develop Work Plan |  |  |  |  |  |  |  |  |
| 2.2 | Develop Project Control Plan |  |  |  |  |  |  |  |  |
| 2.3 | Finalize Project Plan and Gain Approvals |  |  |  |  |  |  |  |  |
| 3 | Execute and Control |  |  |  |  |  |  |  |  |
| 3.1 | Design Framework |  |  |  |  |  |  |  |  |
| 3.2 | Build the Framework |  |  |  |  |  |  |  |  |
| 3.3 | Test the Framework |  |  |  |  |  |  |  |  |
| 3.4 | Implement Framework |  |  |  |  |  |  |  |  |
| 4 | Close the Project |  |  |  |  |  |  |  |  |

Project Schedule

The project schedule includes milestones, task dependencies, task duration, delivery dates, and staff resources assigned to complete the tasks.

|  | Project Management Improvement Project – Phase 1 | Effort Estimate in Days | Planned Start Date | Planned End Date | Resource |
| --- | --- | --- | --- | --- | --- |
| 1 | Initiate Project |  | 02/02/2026 | 02/27/2026 |  |
| 1.1 | Develop Project Charter |  |  |  |  |
| 1.1.1 | Define Scope | 0 | 02/02/26 | 02/05/26 | V. Urbanskyi, D. Pavliuk |
| 1.1.2 | Define Requirements | 8.00 | 02/02/26 | 02/10/26 | V. Urbanskyi, D. Pavliuk |
| 1.1.3 | Identify High-Level Roles | 9.00 | 02/02/26 | 02/11/26 | V. Urbanskyi |
| 1.1.4 | Develop High-Level Budget | 10.00 | 02/02/26 | 02/12/26 | V. Urbanskyi |
| 1.1.5 | Identify High-Level Control Strategies | 1.00 | 02/11/26 | 02/12/26 | V. Urbanskyi |
| 1.1.6 | Finalize Charter and Gain Approvals | 2.00 | 02/11/26 | 02/13/26 | V. Urbanskyi |
| 1.1.6.1 | Consolidate and Publish Project Charter | 11.00 | 02/13/26 | 02/24/26 | V. Urbanskyi |
| 1.1.6.2 | Hold Review Meeting | 11.00 | 02/16/26 | 02/27/26 | V. Urbanskyi |
| 1.1.6.3 | Revise Project charter | 12.00 | 02/16/26 | 02/28/26 | V. Urbanskyi |
| 1.1.6.4 | Gain approvals | 4.00 | 02/26/26 | 02/30/26 | V. Urbanskyi |
| 2 | Plan Project | 24 | 03/02/2026 | 03/26/2026 |  |
| 2.1 | Develop Work Plan |  |  |  |  |
| 2.1.1 | Develop Work Breakdown Structure | 4.00 | 03/02/26 | 03/06/26 | V. Urbanskyi |
| 2.1.2 | Develop Project Staffing Plan | 9.00 | 03/07/26 | 03/16/26 | V. Urbanskyi |
| 2.1.3 | Develop Project Schedule | 2.00 | 03/12/26 | 03/14/26 | V. Urbanskyi |
| 2.1.4 | Develop Project Budget | 5.00 | 03/15/26 | 03/20/26 | V. Urbanskyi |
| 2.2 | Develop Project Control Plan |  |  |  |  |
| 2.2.1 | Develop Communication Plan | 3.00 | 03/15/26 | 03/17/26 | V. Urbanskyi |
| 2.2.2 | Develop Quality Management Plan | 1.50 | 03/17/26 | 03/21/26 | V. Urbanskyi |
| 2.3 | Finalize Project Plan and Gain Approvals | 5.00 | 03/22/26 | 03/29/26 | V. Urbanskyi |
| 3 | Execute and Control Project |  |  |  |  |
| 3.1 | Design Framework |  |  |  |  |
| 3.1.1 | Define framework stages and activities | 5.00 | 04/01/26 | 04/15/26 | V. Urbanskyi, D. Pavliuk |
| 3.1.2 | Design framework content formats | 1.00 | 04/16/26 | 04/18/26 | V. Urbanskyi |
| 3.1.3 | Design web framework delivery tool | 2.00 | 04/19/26 | 04/31/26 | V. Urbanskyi |
| 3.2 | Build the Framework |  |  |  |  |
| 3.2.1 | Write the framework content | 65.00 | 05/01/26 | 06/31/26 | V. Urbanskyi |
| 3.2.2 | Review framework content for quality | 12.00 | 05/15/26 | 06/21/26 | V. Urbanskyi, D. Pavliuk |
| 3.2.3 | Build web tool prototype | 20.00 | 04/19/26 | 04/31/26 | V. Urbanskyi, D. Pavliuk |
| 3.3 | Test the Framework |  |  |  |  |
| 3.3.1 | Test usability of web tool | 4.00 | 05/19/26 | 06/25/26 | D. Pavliuk |
| 3.3.2 | Test usability of content | 4.00 | 06/19/26 | 06/25/26 | D. Pavliuk |
| 3.3.3 | Adjust framework based on user feedback | 5.00 | 06/18/26 | 06/30/26 | V. Urbanskyi, D. Pavliuk |
| 3.4 | Implement Framework |  |  |  |  |
| 3.4.1 | Move framework to production environment | 5.00 | 06/14/26 | 06/19/26 | V. Urbanskyi |
| 3.4.2 | Announce availability of framework | 0.50 | 06/21/26 | 06/25/26 | V. Urbanskyi |
| 4 | Close the Project |  |  |  |  |
| 4.1 | Conduct Post-Project Review | 5.00 | 06/26/26 | 06/29/26 | V. Urbanskyi, D. Pavliuk |
| 4.2 | Celebrate | 0.50 | 06/30/26 | 06/30/26 | V. Urbanskyi, D. Pavliuk |

## 2.4 Project Budget

The project budget describes cost and budget needed to complete the project tasks.  It may include cost and budget for ongoing support after project completion.

Budget during the life of the Project

The budget below provides the detail estimates for labor, material and other items for the duration of the project.

| Line Item | FY05-06 |  |  |  | FY06-07 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Labor | Material | Other | FY Total | Labor | Material | Other | FY Total |
| Phase I |  |  |  |  |  |  |  |  |
| 1. Initiate Project |  |  |  |  |  |  |  |  |
| 1.1 Develop Project Charter | $8,600 | $0 |  | $8,600 | $0 | $0 | $0 | $0 |
| 2. Plan the Project |  |  |  |  |  |  |  |  |
| 2.1 Develop Work Plan |  |  |  |  |  |  |  |  |
| 2.2 Develop Project Control Plan | $15,000 | $0 |  | $15,000 | 2,000 | $0 | $0 | $2,000 |
| 2.3 Finalize Project Plan | $5,000 | 0 |  | $5,000 | $0 | $0 | $0 | $0 |
| 3. Execute and Control Project |  |  |  |  |  |  |  |  |
| 3.1 Design Framework | $5,000 | $0 |  | $5,000 |  |  |  |  |
| 3.2 Build Framework | $65,000 | $0 | $2000 | $67,000 | 20,000 | $0 | $0 | $20,000 |
| 3.3 Test the Framework | $30,000 | $0 | $0 | $30,000 | 10,000 | $0 | $0 | $10,000 |
| 3.4 Implement the Framework | $0 | $0 | $0 | $0 | $4,500 | $0 | $0 | $4,500 |
| 4. Close the Project | $0 | $0 | $0 | $0 | $5,000 | $0 | $0 | $5,000 |
| Total | $128,600 | $0 | $2,000 | $130,600 | $41,500 | $0 | $0 | $41,500 |
| Total Project Budget $172,100 |

Comments: “Other”  is the budget estimate for a training class: Effective Writing for the Web

### On-going Support Budget after Project Completion

The on-going support budget is the detail estimates for on-going support after project completion.

| Line Item | FY05-06 | FY06-07 | Total Budget |
| --- | --- | --- | --- |
| Support Labor | $5,000 | $5,000 | $10,000 |
| Total Two-Year Support Budget | $5,000 | $5,000 | $10,000 |

Comments: Support Labor includes an estimate for minimal support provided for case escalation from Help Desk assistance to users of the Project Management Advisor web site and an estimate for a staff resource to make small updates or corrections if problems are found.

# 3. Project Control Plans

Project Control Plans provide the basis to control and monitor the progress of the project.

The Project Control Plan includes the following detail plans that can be found in the Appendixes:

## 3.1 Communications Plan

Defines the information needs of the project stakeholders and the project team by documenting what, when, where, and how information will be distributed.  See Appendix B.

## 3.2 Quality Management Plan

Provides a plan that defines the quality control and quality assurance activities to be performed during the course of the project and the resources responsible for project quality control and quality assurance activities.  See Appendix C.

## 3.3 Change Management Plan

Provides a plan that helps control the effect of changes during the execute and control stage, thereby avoiding overruns in cost and schedule, incoherent scope, poor quality, etc.  See Appendix D.

## 3.4 Issue Management Plan

Provides a plan that brings visibility to issues, accountability as to how issues are acted upon and helps ensure issues are resolved effectively and in a timely manner.  See Appendix E.

## 3.5 Risk Management Plan

## Provides a plan that helps assure satisfactory project results by identifying project risks and factors that may cause each risk to be realized, specifying a process to follow during the Execute and Control Stage for detecting the occurrence of these factors, and specifying a process for responding to the resulting realized risks.  See Appendix F.
Appendix

## A – Review Team

## Link to separate document.

## B – Communications Plan

## Link to separate document.  (See example provided in PMA.)

## C – Quality Management Plan

## Link to separate document.  (See example provided in PMA.)

## D – Change Management Plan

## Link to separate document.  (See example provided in PMA.)

## E – Issue Management Plan

## Link to separate document.  (See example provided in PMA.)

## F – Risk Management Plan

## Link to separate document.  (See example provided in PMA.)